## Cover Page
Cybersecurity Risk Register
New Nile Bank
| Classification: | Confidential
| Version: | 1.0
| Date: | 2026-04-07

## Data Validation (hidden)
Please select a scope of risk | Please select a risk treatment | Choose Classification | 1 | Please select overall inherent risk rating | Please select a threat
IT assets | Risk Mitigation | Top Secret | 2 | Critical | Credential compromise
Business process | Risk Avoidance | Secret | 3 | High | Insider threats
Personnel | Risk Transfer | Confidential | 4 | Medium | Asset compromise
| Risk Acceptance | Public | 5 | Low | Social engineering
|  |  |  | Very Low | Data breach/leakage
|  |  |  | N/A | Loss of business continuity
Data loss
Mistaking compliance for protection
Regulatory fines
Outdated hardware
Vulnerable software
Cloud vulnerabilities
Ransomware
Malware
Attacks on IoT devices
Operational downtime
DDoS
Underestimation of risk occurrence probability
Partial risk assessment
Improper risk management
Improper incident response
Third party exposure

## Version control
Document Control
Classification
Confidential
Version control
Version | Date | Updated By | Version Details
1 | 2026-07-04 | Samara Risha | First version of the Risk assessment

## Risk register legend
Legend
Column name | Description
Risk identifier | Unique number assigned to Risk
Risk area (scope of risk) | Area in which the risk was identified
Risk owner | Head of organization or asset and process owner for which a risk was identified
Date of risk identification | Date of risk identification
Description of the risk | Risk description
Risk cause | Description of the cause of the inherent risk
Threat | Description of the threat arising from the risk
Risk analysis and consequences | Description of the possible consequences of the risk and information about the timescale in which they can happen.
Date of risk analysis and evaluation | Last date when risk has been identified and assessed
Inherent risk likelihood (1-5) | Quantitative evaluation of the inherent risk likelihood
Inherent risk magnitude/impact (1-5) | Quantitative evaluation of the inherent risk magnitude/impact
Overall inherent risk rating | Overall evaluation of the inherent risk (calculated automatically)
Is the overall inherent risk rated OK? If not please provide a reason | Information whether the risk owner accepts the risk evaluation or not and reason description in case of a mismatch
Updated overall inherent risk rating (manual override) | Overall evaluation of inherent risk and need for treatment actions provided manually by the risk owner in case of a mismatch
Type of treatment action | Type of treatment action chosen for the risk
Risk treatment description | Description of treatment actions which will be taken
Owner of the treatment action | Person responsible for implementing and monitoring of the treatment action
Deadline for action | Deadline for implementing the treatment action
Residual risk description | Residual risk description
Residual risk likelihood (1-5) | Quantitative evaluation of the residual risk likelihood
Residual risk magnitude/impact (1-5) | Quantitative evaluation of the residual risk magnitude/impact
Overall residual risk rating | Overall evaluation of the residual risk (calculated automatically)
Following steps description | Description of the steps which will follow implementation of the treatment action
Last evaluation date | Date of last evaluation of the residual risk
Comment | Place for any additional related comments (for example description of relation between different risks)

## Risk register
Confidential
6:29
Risk register
| Risk identifier | Risk area (scope of risk) | Risk owner | Date of risk identification | Description of the risk | Risk cause | Threat | Risk analysis and consequences | Date of risk analysis and evaluation | Inherent risk likelihood (1-5) | Inherent risk magnitude/impact (1-5) | Overall inherent risk rating | Updated overall inherent risk rating (manual override) | Type of treatment action | Risk treatment description | Owner of the treatment action | Deadline for action | Residual risk description | Residual risk likelihood (1-5) | Residual risk magnitude/impact (1-5) | Overall residaul risk rating | Following steps description | Last evaluation date | Comment
| 1 | IT assets | Ibrahim Gamal | 2025-02-22 | Finanicial Loss unauthorized transactions | Lack of input validation/sanitization in OFS messages | Vulnerable software | Injecting crafted OFS requests to bypass validation and perform unauthorized transfers | 2025-02-23 | 5 | 5 | Critical | Critical | Risk Mitigation | The risk will be mitigated by implementing strict input validation on OFS messages, enforcing strong authentication and authorization controls, restricting access to OFS interfaces, and enabling continuous monitoring and logging of transactions.” | Sara Asharaf Ibrahim Gamal | 2026-02-28 | There will still be risk and the Temons team must provide a comeplete mitigation for it | 2 | 5 | Medium | Monitor implementation of the controls and residual risk | 2025-02-23 | N/A
| 2 | IT assets | Ibrahim Gamal | 2025-02-22 | Data breaches (customer/account data exposure) | Lack of input validation/sanitization in OFS messages | Data breach/leakage | The Customer data will be exposed leading to reputaional damage | 2025-02-23 | 5 | 4 | critical | Critical | Risk Mitigation | The risk will be mitigated by implementing strict input validation on OFS messages, enforcing strong authentication and authorization controls, restricting access to OFS interfaces, and enabling continuous monitoring and logging of transactions.” | Sara Asharaf Ibrahim Gamal | 2026-02-28 | There will still be risk and the Temons team must provide a comeplete mitigation for it | 2 | 5 | Medium | Monitor implementation of the controls and residual risk | 23/02/2025
. | 3 | IT assets | Ibrahim Gamal | 2025-02-22 | Regulatory penalties | Lack of input validation/sanitization in OFS messages | Non Compliant with CBE - PCI | Fines will be applied if the risk is mitigated | 2025-02-23 | 4 | 3 | High | High | Risk Mitigation | The risk will be mitigated by implementing strict input validation on OFS messages, enforcing strong authentication and authorization controls, restricting access to OFS interfaces, and enabling continuous monitoring and logging of transactions.” | Sara Asharaf Ibrahim Gamal | 2026-02-28 | There will still be risk and the Temons team must provide a comeplete mitigation for it | 2 | 5 | Medium | Monitor implementation of the controls and residual risk | 23/02/2025
. | 4 | IT assets | Ibrahim Gamal | 2025-04-03 | Unauthirzed administrative access | Reflected XSS attackers can use to steel session tokens from the embloyees in the browser of T24 | Vulnarabile Sosfrware | Stealing the session cookies from the embloyees can lead to unauthirzed administrative access | 2026-05-03 | 5 | 5 | critical | Critical | Risk Mitigation | apply the Input Validation untill we can Installing the latest updates and patches of T24 | Ibrahim Gamal Samara Risha | 2026-10-03 | The inpult validation can reduce the risk but still won't be affective until we install the latest updated version | 3 | 3 | medium | Monitor implementation of the controls and residual risk and installing the updates | 2026-11-03
. | 5 | IT assets | Hossam Badr | 2025-10-03 | Unzuthirzed access to the DB | Overpriveliged users | Insider threat | Some users with lower privilges usually get higher priviliges | 2025-11-03 | 3 | 5 | Critical | Critical | Risk Mitigation | We should apply the Least privilage principle and applying the permission approval policy when giving user's higher priviliges | Hossam Badr Mohamed Rgab | 14/3/2025 | When applying the the principle and the policy , it will reduce the risk and nearly eliminate it | 1 | 1 | Very low | Implementing the the controls mentioned in the risk treatment document | 15/3/2026
. | 6 | IT assets | Amira Zaki | 20/7/2025 | Data theft / Unzuthrized access / Creidentials theft | Lack of Awareness , Email gateway can't fully detect phising emails | APT planning to start a phising campagin , sending mailcous emails to the customers | Successful attempts can lead to the employees crediential theft or data leakge or downloading mailcous files that will harm the system | 21/7/2025 | 4 | 4 | Critical | Critical | Risk Mitigation | Conducting awareness sessions to the employees | Amira Zaki Samara Risha | 30./8/2025 | sending the employees warning through their emails about the phishing campaings until we start conducting the awareness | 2 | 2 | Low | Start conducting the awareness sessions | 24/7/2025
. | 7 | IT assets | Nour Eldin | 2026-10-08 | ATM Network – 18 ATMs running Windows 10 IoT End-of-Life OS. No security patches available. | Ne Security Patches Avilable | Any undiscovered Vulnrababilites can be exploited |  | 2026-11-08 | 5 | 5 | Critical | Critical | Risk Mitigation |  | Nour Eldin | 26/10/2026 | It won't work that much cuz we still need the updates | 4 | 4 | Critical | Installing the updates | 15/8/2026
. | 8 | IT assets | Nader Saleh | 20/8/2026 | There is a risk that an attacker will exploit the pinning bypass vulnerability during a MITM attack. | \Certificate Pinning Bypass (The app fails to strictly validate the server’s unique identity, or the pinning mechanism is easily disabled by tools like Frida | APTs and Skilled threat actors can bybasse the certificates of the users | This would result in the exposure of sensitive Cardholder Data (CHD) and Authentication Credentials in plain text. | 21/82026 | 5 | 5 | Critical | Critical | Risk Mitigation | Development team to implement strict certificate pinning in next mobile app release (v3.2). | Nader Saleh | 30/8/2026 |  | 3 | 3 | Medium | Development team to implement strict certificate pinning in next mobile app release (v3.2). | 25/8/2026
. | 9 | [11 empty] | Please select overall inherent risk rating
. | 10 | [11 empty] | Please select overall inherent risk rating
. | 11 | [11 empty] | Please select overall inherent risk rating
. | 12 | [11 empty] | Please select overall inherent risk rating
. | 13 | [11 empty] | Please select overall inherent risk rating
. | 14 | [11 empty] | Please select overall inherent risk rating
.+26:29 | 15 | [11 empty] | Please select overall inherent risk rating
. | 16 | [11 empty] | Please select overall inherent risk rating
. | 17 | [11 empty] | Please select overall inherent risk rating
. | 18 | [11 empty] | Please select overall inherent risk rating

## Heat map
Confidential
Inherent risk register heat map | [6 empty] | Residual risk register heat map
Risk impact | Critical | 0 | 0 | 1 | 0 | 4 | Risk impact | Critical | 0 | 3 | 0 | 0 | 0
| High | 0 | 0 | 0 | 1 | 1 |  | High | 0 | 0 | 0 | 1 | 0
| Medium | 0 | 0 | 0 | 1 | 0 |  | Medium | 0 | 0 | 2 | 0 | 0
| Low | 0 | 0 | 0 | 0 | 0 |  | Low | 0 | 1 | 0 | 0 | 0
| Very low | 0 | 0 | 0 | 0 | 0 |  | Very low | 1 | 0 | 0 | 0 | 0
|  | Very low | Low | Medium | High | Critical |  |  | Very low | Low | Medium | High | Critical
|  | Risk likelihood | [6 empty] | Risk likelihood

## Overall risks
Confidential

## Summary of risks (hidden)
Inherent risk |  | Residual risk
Critical | 7 | Critical | 1
High | 1 | High | 0
Medium | 0 | Medium | 5
Low | 0 | Low | 1
Very Low | 0 | Very Low | 1